LSE MBA ESSENTIALS  ·  CAPEX PROJECT GOVERNANCE

DECISION BRIEF

Final Investment Decision

FID

Stage-gate playbook, FID package contents, LSE appraisal (NPV / IRR / payback / ARR), debiasing protocols and governance checklists.

| Item | Content |
| --- | --- |
| Document | Methodological brief + template for the FID package |
| Author / owner | Francois Philippe Amour Dorleans |
| Academic anchor | LSE — MBA Essentials (Feb–Apr 2023), cert. 342406 |
| Operating anchor | Capex project management, Front-End Loading, stage-gate |
| Audience | Investment committee, sponsor, PMO, project team |
| Status | Working standard — instantiate on a named project |
| Language version | English counterpart of the French dossier |
| Date | 11 September 2026 |

LSE golden rule before opening the file A long-term investment decision must maximise shareholder wealth. Judge cash flows, not accounting profit. NPV is the most accurate method because it incorporates the time value of money. Study costs already spent are a sunk cost: they never justify a bad FID.

# Contents

1. Purpose, audience and how to use this brief

2. What FID is — and why it changes everything

3. LSE MBA Essentials — what belongs inside a FID

4. Stage-gate architecture to FID

5. Gate 0 — Identify / Appraise / FEL-1

6. Gate 1 — Select / Pre-feasibility / FEL-2

7. Gate 2 — Define / FEED / Feasibility / FEL-3

8. Gate 3 — The FID

9. Standard FID package (committee file)

10. Investment appraisal — how the numbers must be built

11. Risk, sensitivities and scenarios

12. Cognitive biases and debiasing (LSE Module 8)

13. Governance, roles and RACI

14. Master pre-FID checklists

15. After FID — what the brief must already specify

16. CV, interview and sponsor one-pager language

17. Annexes — glossary, formulae, sources, project sheet

Seventeen sections: stage-gate playbook + committee-file template + checklists. Instantiate on a named asset before sending to committee.

# 1. Purpose, audience and how to use this brief

This document has two jobs. First, it explains how to build the path to FID. Second, it specifies what the investment committee must receive in order to decide. It is therefore both a methodological playbook and a template for the FID package.

It deliberately joins two bodies of knowledge that are too often kept apart: the MBA toolkit (appraisal, ratios, decision biases, value creation) and capex project management (stage-gate, FEL, FEED, estimating, contracts, permits). A FID is neither an engineering deliverable nor a spreadsheet. It is an irrevocable allocation of capital under uncertainty.

## 1.1 What this brief is not

- A ready-to-fill financial model for a named asset (produce that as a project annex).

- A technical FEED (FEED is an input to FID, not the FID).

- Authorisation to sign EPC contracts before independent review.

## 1.2 How to use it

- Read sections 2 to 4 to align committee language (FID, gates, NPV).

- Instantiate sections 5 to 8 on the live project (deliverables, uncertainty, risks).

- Use section 9 as the table of contents of the committee binder.

- Run the section 14 checklists before sending the file to the committee secretariat.

- Keep section 16 for interviews and the CV: same vocabulary, same discipline.

# 2. What FID is — and why it changes everything

The Final Investment Decision is the governance gate at which the competent authority (board, investment committee, joint venture) commits the major execution capital. Before FID, the organisation buys knowledge (studies, options, FEED). After FID, it buys reality (long-lead equipment, EPC, construction, commissioning).

Managerial consequence: FID quality is judged by promised vs delivered three to five years later (capex, schedule, cash flows, HSE, ESG), not by enthusiasm in the room on decision day.

## 2.1 Before / at / after FID

|  | Before FID | At FID | After FID |
| --- | --- | --- | --- |
| Nature of spend | Studies, options, FEED | Capex commitment + launch opex | Execute, commission, operate |
| Typical cost uncertainty | ±50%, then ±30%, then ±10–15% | Commitment-class estimate | Control vs baseline |
| Governance question | Should we keep studying? | Do we commit the capital? | Are we delivering the promised value? |
| Possible outcome | Go / Recycle / Kill | Approve / Defer / Reject | Change control, lookback |
| Dominant bias | Overconfidence, champion bias | Sunk-cost, confirmation | Planning fallacy realised |

Table 1 — FID as a change of spending regime and governance regime.

## 2.2 The three committee outcomes

- Approve. Execution budget is opened, often with conditions precedent (financial close, final permit, partner FIDs, hedges).

- Defer / Recycle. The project can still create value, but timing, price, scope or funding are not mature. Do not kill it: send it back to the previous gate.

- Reject / Kill. NPV is not robust, risk is uninsurable, capital has a better use elsewhere, or there is no strategic fit.

LSE discipline — sunk-cost fallacy (Module 8) The millions already spent on pre-feasibility and FEED are irrecoverable. They do not enter the FID calculation. The committee judges the remaining project: future cash flows versus capex still to be committed, discounted at the required rate. Continuing 'because we have invested too much in studies' is precisely the error LSE teaches you to avoid.

# 3. LSE MBA Essentials — what belongs inside a FID

The LSE MBA Essentials certificate (February–April 2023) does not use the word FID. It does, however, supply the entire judgement system that a FID requires. The mapping below is what you quote in committee and in interviews.

## 3.1 Modules used

| LSE module | Concept | Use on the path to FID |
| --- | --- | --- |
| M3–M4 Strategy | Value chain, advantage, make-or-buy, M&A | Why this project, now; concept options |
| M5 Accounting | P&L, balance sheet, cash flows, basic ratios | Read the balance-sheet / liquidity impact of capex |
| M6 Management accounting | Budgets, costs, life-cycle, target costing | Capex + opex + decommissioning; design-to-cost |
| M6 Unit 4 | ARR, Payback, NPV, IRR | Core of the investment-appraisal pack |
| M7 Advanced ratios | Margin, ROA, ROE, current, gearing | Post-FID balance-sheet strength, covenants |
| M8 Decision | Biases, planning fallacy, sunk cost | Pre-mortem, outside view, challenge |
| M1 / M10 Leadership | Influence, culture, accountability | Sponsors, committee, cold-eye review |

Table 2 — MBA Essentials mapped onto FID practice.

## 3.2 The four appraisal methods (LSE Module 6 Unit 4)

LSE learning outcomes: calculate rates of return on investment opportunities; select the best opportunity. Teaching assumptions in the course (to be lifted in a live FID): cash flows estimable with relative certainty; no tax or inflation in the examples; cash flows treated as occurring on the last day of each period.

### NPV — primary criterion

Unlike ARR and payback, NPV takes the timing of cash flows into account. Each flow is discounted at the required rate r (opportunity cost / WACC / hurdle), then summed.

NPV = Σ CFn / (1+r)^n  (including I0 at n = 0). Rule: NPV > 0 means the investment beats the alternative placement at rate r. Between two positive-NPV projects, retain in principle the higher NPV (wealth creation), subject to capital rationing and risk.

LSE verdict: “Net present value is a better method […] as it makes use of cash flows instead of profit, and takes the timing of these cash flows into account.”

### IRR — acceptance test versus hurdle

IRR is the rate that drives NPV to zero. LSE rule: accept if IRR exceeds the rate at which the money could otherwise have been invested. Operating caveat (to add to the course): IRR can mislead across projects of different scale or cash-flow shape; NPV remains the judge of value creation.

### Payback — liquidity screen, not king

Cumulative cash flows are tracked until the initial outlay is recovered. LSE: if payback exceeds the maximum set by management, reject; between two acceptable projects, the shorter payback wins. Taught limits: no time value of money; a project that creates more wealth later can be wrongly discarded.

### ARR — secondary accounting indicator

ARR = (average annual operating profit / average investment) × 100. LSE flags two weaknesses: it uses accounting profit, not cash flows; it ignores the time value of money. Useful only if the board still asks for it; never as the sole FID criterion.

## 3.3 What LSE adds beyond the formulae

- Purpose of the decision: maximise shareholder wealth, not 'launch a project'.

- Long-term asset decisions have lasting financial consequences — hence stage-gate.

- Risk must be judged, not return alone (Module 6 closing note).

- Life-cycle costing: pre-production, production, post-production (decommissioning, environment, after-sales).

- Target costing / design-to-cost: start from the price the market will pay, minus required margin, to constrain capex.

- Debiasing is mandatory: the inside view is too optimistic; use outside view + pre-mortem + accountability.

# 4. Stage-gate architecture to FID

Stage-gate (Cooper) and Front-End Loading (IPA / extractives and infrastructure) say the same thing: do not buy execution with an idea. Each gate has a deliverable, an estimate class, a governance question and a right to kill the project.

## 4.1 Language mapping

| This brief | Oil & gas / IPA | Infra / utilities | PMI (approx.) | Typical cost uncertainty |
| --- | --- | --- | --- | --- |
| G0 Identify | FEL-1 Appraise | Opportunity / need case | Initiating | ±50% (Class 5) |
| G1 Select | FEL-2 Select | Pre-feasibility / options | Planning early | ±30% (Class 4) |
| G2 Define | FEL-3 Define / FEED | Feasibility / detailed design | Planning late | ±10–15% (Class 3) |
| G3 FID | FID | Financial close / sanction | End of Planning | Commitment baseline |
| Execute | Execute | Construction | Executing | EAC control |

Table 3 — FEL / infrastructure / PMI translation. Adapt the labels to your committee jargon, not the logic.

## 4.2 Economics of information

Spend 1 to 5% of final capex on studies to reduce uncertainty before committing 100. A weak FEED statistically predicts post-FID overrun. Front-end loading quality (FEL index) predicts success more reliably than sponsor enthusiasm.

# 5. Gate 0 — Identify / Appraise / FEL-1

Objective: a strategic problem or opportunity, not yet a project. You are seeking the right to spend study money, not the right to build.

5.1 Work to complete

- Need statement: operating constraint, market, regulation, decarbonisation, asset replacement, growth.

- Strategic fit and value chain: where does the project create advantage (cost, differentiation, real option)?

- Crude option screening, including 'do nothing' and 'defer'.

- Order-of-magnitude capex / opex / revenue (±50%).

- Explicit kill criteria (if even a reasonable scenario cannot create value).

- Stakeholder map, in-principle permits, HSE / ESG red flags.

- Governance: named sponsor, PMO, Gate 1 study budget.

## 5.2 Gate deliverable and decision

Deliverable: Opportunity brief (4 to 8 pages) + options sheet. Decision: Go to Select / Recycle / Kill.

Biases to watch: champion bias (judging the person, not the file); representativeness ('it looks like a success, so it will work'); status quo (launching so the portfolio does not have to change).

# 6. Gate 1 — Select / Pre-feasibility / FEL-2

Objective: a preferred option that can already be compared, with a still-fragile but discriminating business case. Do not open FEED unless the option survives an external look.

## 6.1 Work to complete

- Comparative concept studies: capacity, site, technology, make-or-buy, phasing, partners.

- First Class 4 capex/opex estimate (±30%), including offsites and owner's costs.

- Economic sketch: cash flows, indicative NPV/IRR, payback, working-capital need.

- Outside view (Lovallo & Kahneman, LSE M8): reference class of comparable projects.

- Major risks, permits, connections, HSE, ESG, social acceptability.

- First contract and financing strategy (debt / equity / JV).

- Design-to-cost: LSE target costing if the market sets the price.

## 6.2 Outside-view protocol — five LSE steps

- Select a reference class broad enough to be statistical, narrow enough to be comparable.

- Map the outcome distribution (median, clusters, cost / schedule / NPV outliers).

- Place your project intuitively in that distribution (inside view).

- Assess how reliable your past forecasts of this type have been.

- Correct the estimate toward the class mean: the less reliable the forecast, the more you regress to the mean.

LSE example: the Scottish Parliament estimated at £10–40m for 2001, delivered at £414m in 2004. That is the planning fallacy as public monument. A FID that ignores the reference class repeats the same error.

## 6.3 Gate deliverable and decision

Deliverable: Concept select report + preliminary business case + Gate 1 risk register. Decision: authorise FEED (budget and duration capped) / Recycle options / Kill.

# 7. Gate 2 — Define / FEED / Feasibility / FEL-3

Objective: an executable project. This is roughly 80% of the intellectual work before FID. A FID file without a mature FEED is not a FID: it is a request for a blank cheque.

## 7.1 Engineering and scope

- Frozen design basis: capacity, availability, product specs, codes, site assumptions.

- FEED: PFDs/P&IDs or sector equivalent, plot plan, key MTOs, interfaces, utilities.

- Long-lead items identified; procurement lead times on the critical path.

- WBS and scope dictionary: in, out, and 'to be decided before FID'.

- Constructability, operability, maintainability, commissioning philosophy.

## 7.2 Estimating and schedule

- Class 3 estimate (±10 to 15%): capex, owner's costs, spares, commissioning, contingency.

- Typical-year opex + ramp-up + life-cycle (LSE total life-cycle costing, including post-production).

- Integrated Level 2/3 schedule, critical path, float, construction seasonality.

- Contingency calibrated to risk (not a political cushion). Escalation and change allowance held separately.

## 7.3 Contracts, permits, HSE, ESG, financing

- Contract strategy: lump-sum EPC, EPCM, packages, alliance — risk allocation written down.

- Draft contracts ready to sign the day after FID (or a dated negotiation path).

- Permits / land / connections: status, critical path, conditions precedent.

- HSE case, environment, social, climate: commitments and associated opex costed.

- Financing structure: term sheet, covenants, gearing and liquidity impact (LSE M7).

- Owner team: execution organogram, critical hires, project assurance.

## 7.4 Mandatory pre-mortem before the file is sent

LSE / Klein / Kahneman protocol: “Imagine we are one year into the future. We implemented the plan as it now exists. The outcome was a disaster. Please take 5 to 10 minutes to write a brief history of that disaster.”

This forces consider-the-opposite, bypasses group censorship once a plan feels 'too advanced', and feeds the FID risk register. Typical causes to surface: policy reversal, sponsor departure, underestimated interfaces, commodity price, contractor underperformance, permits.

# 8. Gate 3 — The FID

The committee is not 'validating a slide deck'. It is allocating capital. Session quality depends on package quality and challenge quality.

## 8.1 Questions the committee must ask

- What is NPV at WACC / hurdle, and what happens if capex +15%, schedule +12 months, price −20%?

- Does IRR really beat opportunity cost, or only the team's base case?

- What is payback, and do we have the liquidity to fund the cash trough?

- Which external reference class justifies cost and schedule? (outside view)

- What did the pre-mortem teach us? What would actually destroy value?

- Is scope frozen? How many hold points remain open?

- Are permits and financing clear conditions precedent?

- What is the balance-sheet impact: gearing, current ratio, covenants, rating?

- Why now, and what is the option value of waiting?

- If we have 100 of scarce capital, is this still the best use?

## 8.2 Typical conditions precedent

- Financial close / syndication / partner equity call.

- Determining permit obtained, or drop-dead date.

- Mirror FID of co-investors.

- Price / FX hedge if the model requires it.

- EPC contracts signed inside an authorised envelope.

# 9. Standard FID package (committee file)

The package is a binder, not a novel. Each tab has an owner, a freeze date and a status (final / draft / N/A). Copy the contents list below into the project workspace.

## 9.1 Binder architecture

| Tab | Content | Typical owner |
| --- | --- | --- |
| 00 Decision note | 3-page recommendation: Go / Recycle / Kill + conditions | Sponsor |
| 01 Strategic fit | Problem, discarded options, advantage, timing | Strategy / Sponsor |
| 02 Scope & FEED | Design basis, exclusions, FEL maturity | Engineering |
| 03 Capex / opex / schedule | Class 3, contingency, critical path | Controls / Cost |
| 04 Business case | Cash flows, NPV, IRR, payback, ARR if required | Project finance |
| 05 Sensitivities & scenarios | Tornado, downside, rupture | Finance / Risk |
| 06 Risks & insurance | Register, pre-mortem, policies | Risk |
| 07 Contracts | Strategy, allocation, negotiations | Contract / Legal |
| 08 Permits HSE ESG | Status, gaps, compliance opex | HSE / Permitting |
| 09 Financing & balance sheet | Term sheet, gearing, covenants, liquidity | Treasury / CFO |
| 10 Execution organisation | Owner team, RACI, post-FID KPIs | Project Director |
| 11 Independent assurance | Cold-eye review, closed actions | PMO / IA |
| 12 Annexes | Model, letters, prior-gate minutes | PMO |

Table 4 — Recommended FID package structure.

## 9.2 The decision note (three pages maximum)

Page 1: context, recommendation in one sentence, capital ticket requested, base-case and downside NPV/IRR/payback. Page 2: five value-killing risks and mitigations. Page 3: conditions, commitment timetable, explicit ask of the committee. Everything else goes to annexes. A committee that has to hunt for the recommendation across 80 slides has already lost.

## 9.3 What Finance must certify in tab 04

- Operating cash flows, not net accounting profit (LSE).

- Complete I0: capex, owner's costs, working capital, tax credits, grants, residual value.

- Explicit rate r: group WACC, divisional hurdle, or risk-adjusted project rate — and why.

- Tax, inflation, FX: written assumptions (this is where LSE teaching simplifications are lifted).

- Consistency with Module 7 ratios: the project must not break liquidity or covenants.

- Model audit trail (version, cross-checks, independent review).

# 10. Investment appraisal — how the numbers must be built

This section installs the calculation discipline LSE teaches, then makes it usable in a live committee.

## 10.1 Criterion hierarchy

| Criterion | Question it answers | Status at FID |
| --- | --- | --- |
| NPV @ r | Does the project create wealth? | Primary decision rule |
| IRR vs hurdle | Does return beat opportunity cost? | Secondary decision rule |
| Payback | How fast is cash recovered? | Liquidity control |
| ARR | What average accounting return? | Secondary / reporting |
| Sensitivities | Does NPV survive an imperfect world? | Robustness condition |
| Balance-sheet ratios | Can the group hold after commitment? | Feasibility constraint |

## 10.2 Working formulae

NPV: NPV = Σn [ CFn / (1+r)^n ]. Equivalently, use discount factors from a table (LSE method): PV = CFn × factor(r, n).

ARR: (average annual operating profit / average investment) × 100, with average investment = (I0 + disposal value) / 2.

Uneven payback: track the cumulative; between two years, fraction = residual / next-year flow, converted to months if needed (LSE example: 2 years and 8 months).

IRR: rate such that NPV = 0. In practice: Excel IRR / XIRR, or bracketing by trial (LSE example around 20% then 25%).

## 10.3 LSE teaching mini-case (know it by heart)

Pink Panther Productions — machine £40,000; flows 8 / 15 / 20 / 18 / 8; disposal £7,000 in year 5; 20% opportunity rate. LSE computes a positive NPV of about £3,367. At 25% the NPV turns negative (about −£1,460). IRR is therefore slightly below 25% and above 20%: the project beats the alternative placement. That is exactly the reasoning to hold at FID, with extra zeros.

## 10.4 What a live FID adds to the course example

- Tax, inflation, FX, working capital, decommissioning.

- Phased capex (not a single I0 at n = 0).

- Real options: defer, expand, abandon — sometimes more valuable than a binary Go.

- Cost of capital: group WACC vs divisional hurdle vs project beta.

- Capital rationing: NPV per unit of scarce capital if the budget is capped.

- A distribution, not a point: P50 / P80 of capex and NPV.

## 10.5 Ratio link (Module 7) — the project inside the group

A positive-NPV project can still be refused if it trips a covenant. Before FID, Finance documents the effect on: net margin, ROA, ROE, current ratio, quick ratio, gearing. LSE: 30% gearing is not 'high risk' in itself — it depends on the sector and cash-flow stability. The committee must still see the leverage path through the construction peak, when cash leaves and the asset is not yet productive.

# 11. Risk, sensitivities and scenarios

LSE: “in addition to return on investment, there are also other factors (such as risk)”. A FID package with only a base case is an advocacy file, not a decision file.

## 11.1 Minimum set

- Tornado: NPV vs ± capex, ± price / volume, ± opex, ± schedule, ± rate.

- A credible downside (not a cartoon 'worst case').

- A rupture scenario (permit loss, contractor default, commodity shock).

- Switching values: at what capex or price NPV hits zero.

- Contingency vs management reserve: who holds which pot, who releases it.

## 11.2 Translating risk into governance

Every 'NPV-killing' risk needs an owner, a leading indicator, a post-FID hold point and, where possible, a contract or policy that carries it. A risk with no owner in the package does not exist for the committee: it will explode in execution.

# 12. Cognitive biases and debiasing (LSE Module 8)

Projects die more often from organised optimism than from a wrong formula. The FID file must make countermeasures visible, not only Excel outputs.

## 12.1 Biases that specifically hit the path to FID

| LSE bias | Project symptom | Countermeasure in the file |
| --- | --- | --- |
| Planning fallacy | Base case = best case | Outside view + P80 schedule/cost |
| Overconfidence | Ranges too tight | Calibration, estimate classes |
| Sunk-cost | 'We have spent too much to stop' | NPV on remaining cash only |
| Confirmation | Hunting slides that say yes | Consider the opposite + devil's advocate |
| Champion bias | Voting for the sponsor | Multi-criteria grid / cold-eye |
| Loss aversion | Rejecting a good risk | Frame as value creation, not option loss |
| Status quo | Re-launching the usual | Costed 'do nothing' option |
| Partition dependence | Sprinkling capex evenly | Capital rationed on NPV / risk |

Table 5 — LSE Module 8 biases applied to FID.

## 12.2 Debiasing toolkit to write into the process

Motivation: sponsor accountability in front of the committee (watch the risk of producing 'defensible' files rather than true ones); incentives on forecast quality, not on 'Go'.

Cognition: consider the opposite; five-step outside view; pre-mortem; calibration training (LSE example: Shell geologists trained on past cases).

Design: written independent opinions before the session; individual estimates before group discussion (avoid anchoring); decision analysis if multi-criteria.

# 13. Governance, roles and RACI

A FID without a power architecture produces either zombie projects or political Goes.

## 13.1 Roles

| Role | Responsibility through FID |
| --- | --- |
| Sponsor | Owns the recommendation, protects the kill, owns the lookback |
| Project Director / PM | Integrates scope, cost, schedule, risk, package |
| Project finance | Model, rate, sensitivities, balance-sheet impact |
| Engineering / FEED lead | Technical maturity and exclusions |
| Risk / HSE / ESG | Register, pre-mortem, permits |
| Legal / Contract | Contractual allocation and conditions |
| Treasury / CFO | Funding, covenants, liquidity |
| PMO / Assurance | Gate quality, cold-eye, checklist |
| Investment committee | Decide Approve / Defer / Reject |

## 13.2 Session rules

- File frozen and circulated N days ahead (typically 5 to 10 working days).

- Three-page note read first; annexes only on question.

- A named challenger who is not the project champion.

- Decision minuted, conditions dated, owner for each condition.

- Mandatory lookback 12–24 months after start-up (LSE feedback / calibration).

# 14. Master pre-FID checklists

Do not send the file to the committee secretariat while a critical line is red. 'Desirable' items may stay amber with a dated plan.

## 14.1 Technical maturity and estimate

| Item | Expected status at FID |
| --- | --- |
| Signed design basis | Frozen |
| FEED complete on the commitment scope | Yes |
| Exclusions and interfaces documented | Yes |
| Class 3 estimate (±10–15%) | Yes |
| Contingency derived from risk | Yes |
| Integrated schedule + critical path | Yes |
| Long leads identified and strategised | Yes |

## 14.2 Economics and finance

| Item | Expected status at FID |
| --- | --- |
| Versioned model + audit trail | Yes |
| NPV at published rate, base and downside | Yes |
| IRR vs explicit hurdle | Yes |
| Payback and cash profile (construction trough) | Yes |
| Tax / inflation / FX documented | Yes |
| Gearing, liquidity, covenant impact | Yes |
| Financing aligned or condition precedent | Yes |

## 14.3 Risk, legal, execution

| Item | Expected status at FID |
| --- | --- |
| Pre-mortem held and folded into the register | Yes |
| Outside view / reference class | Yes |
| Cold-eye review closed or actions dated | Yes |
| Contract strategy and draft instruments | Yes |
| Permit critical path + drop-dead | Yes |
| HSE / ESG costed in opex | Yes |
| Owner team named for execution | Yes |
| Conditions precedent drafted | Yes |

# 15. After FID — what the brief must already specify

FID is not the end of management; it is the start of control. The package must therefore contain the execution baseline:

- Budget, schedule and cash-flow reference (against which EAC / ETC will be measured).

- Change control: who can move scope, at what threshold the committee is recalled.

- Hold points (permits, tests, mechanical completion, handover).

- KPIs: safety, cost, schedule, quality, stakeholders, cash forecasts.

- Lookback / benefits realisation: compare actual cash flows with FID promises (organisational calibration).

This is where kaizen costing and TQM (LSE Module 6) take over: once the asset is live, value is defended in operations, not in another NPV slide.

# 16. CV, interview and sponsor one-pager language

Pedagogical purpose of this brief: bed LSE vocabulary into a capex practice you can tell without empty jargon.

## 16.1 CV line (adapt to sector)

“Structured the path to FID through an Identify–Select–Define stage-gate: commitment-grade FEED (±10–15%), NPV/IRR business case vs WACC, sensitivities and pre-mortem to correct planning fallacy, Go / Recycle / Kill recommendation without sunk-cost bias. LSE MBA Essentials (investment appraisal, ratios, decision biases).”

## 16.2 Interview answers — four frequent questions

“What is FID?” — The decision to commit execution capital, not a Gantt phase. Before: you buy information. After: you buy steel and concrete.

“NPV or IRR?” — NPV for wealth creation, IRR for the test versus opportunity cost. In conflict (different scale), NPV wins. Payback for liquidity only.

“Why so many studies?” — Because 2% of capex spent well on FEL avoids 20% overrun. The outside view confirms this more reliably than team optimism.

“What do you do with studies already paid?” — Sunk cost. The committee judges the future. If remaining NPV is negative, you kill, even after a beautiful FEED.

## 16.3 Sponsor one-liner in session

“We request X of commitment. At hurdle r%, base NPV is Y, downside NPV is Z. The three risks that can zero it are A, B and C; they are carried by this contract, this permit, this reserve. Recommendation: Approve subject to conditions 1-2-3.”

# 17. Annexes

## A. Working glossary

| Term | Committee-useful meaning |
| --- | --- |
| FID | Irrevocable commitment of execution capital |
| FEED | Engineering mature enough to estimate and contract |
| FEL | Quality of front-end work (predicts overrun) |
| WACC / hurdle | Discount rate r / minimum required return |
| NPV | Wealth created beyond the cost of capital |
| IRR | Rate that sets NPV to zero |
| Class 3 / 4 / 5 | Estimate uncertainty band |
| Owner's costs | Owner costs outside the EPC contract |
| Contingency | Provision tied to estimated project risks |
| Management reserve | Leadership pot, outside the team baseline |
| Cold-eye | Independent review before the gate |
| Lookback | FID promises versus actuals |

## B. Formula reminders

ARR = (average annual operating profit / average investment) × 100.

Average investment = (initial cost + disposal value) / 2.

Fractional payback = year before crossing + (amount still to recover / flow in the crossing year).

Discount factor = 1 / (1+r)^n.

PV(flow) = flow × factor.  NPV = sum of PVs, including I0.

LSE acceptance rule: NPV > 0; IRR > alternative rate; payback < management maximum.

## C. Teaching sources used

LSE MBA Essentials — Module 6 Unit 4 Investment appraisal techniques (Atrill & McLaney, 2015; Weetman, 2015).

LSE MBA Essentials — Module 6 costing (life-cycle, target costing, kaizen, TQM, benchmarking).

LSE MBA Essentials — Modules 5 and 7, financial statements and ratios (liquidity, efficiency, profitability, gearing).

LSE MBA Essentials — Module 8, biases and debiasing (Kahneman; Lovallo & Kahneman 2003; Klein 2007 pre-mortem; Larrick 2004).

Capex practice: stage-gate, FEL / IPA, AACE estimate classes, investment-committee governance.

## D. Project instantiation (to complete)

| Field | Project value |
| --- | --- |
| Project / asset name |  |
| Sponsor / Project Director |  |
| Current gate |  |
| Capex P50 / P80 |  |
| Rate r / hurdle |  |
| NPV base / downside |  |
| IRR base |  |
| Payback |  |
| Target FID date |  |
| Conditions precedent |  |
| Recommendation | Approve / Defer / Reject |

Table 6 — Page to duplicate at the front of each live project package.

Close — what to remember FID is an allocation of capital under uncertainty. Stage-gate buys information until uncertainty is affordable. LSE supplies the judge (NPV on cash flows, IRR versus opportunity cost, balance-sheet ratios) and the mental discipline (no sunk-cost, outside view, pre-mortem). The rest is execution: frozen scope, honest estimate, contract that carries risk, a committee willing to kill.

Prepared to bed capex practice in the LSE MBA Essentials frame of Francois Philippe Amour Dorleans. Instantiate project by project; do not present this as a signed FID.